## Question
What is the normal duration of the project?
What is the minimum additional cost in which you can complete the project in 120 days?
What methodology can be adopted to solve this practical problem?

## Solution Schedule
WBS ID | Activity | Original Duration | Crash duration | Predecessor ID | Lead/(Lag) | Link with Predecessor | Early Start | Early Finish | Late Start | Late Finish | Total Float | Critical Activity | Crash cost per day | Accelarating days
1 | Building Project
A | Site Handover to Contractor (Start Milestone) | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | Yes | 4000 | 0
1.1 | Structure Work
1.1.1 | Foundation
1.1.1.1 | Excavation | 3 | 1 | A | 0 | FS | 0 | 3 | 0 | 3 | 0 | Yes | 3000 | 2
1.1.1.2 | PCC | 4 | 3 | 1.1.1.1 | 0 | FS | 3 | 7 | 3 | 7 | 0 | Yes | 1000 | 1
1.1.1.3 | Reinforcement & Shuttering | 8 | 7 | 1.1.1.2 | 1 | SS | 4 | 12 | 4 | 12 | 0 | Yes | 3000 | 1
1.1.1.4 | Casting with RCC | 8 | 5 | 1.1.1.3 | 1 | SS | 5 | 13 | 5 | 13 | 0 | Yes | 4000 | 3
1.1.2 | Plinth Level
1.1.2.1 | Columns up to Plinth Beam Bottom | 7 | 4 | 1.1.1.4 | 0 | FS | 13 | 20 | 13 | 20 | 0 | Yes | 4000 | 3
1.1.2.2 | Backfilling & Compaction | 3 | 2 | 1.1.2.1 | 0 | FS | 20 | 23 | 20 | 23 | 0 | Yes | 2000 | 1
1.1.2.3 | Plinth Beam Reinf. & Shuttering | 6 | 5 | 1.1.2.2 | 0 | FS | 23 | 29 | 23 | 29 | 0 | Yes | 1000 | 1
1.1.2.4 | Casting of Plinth Beam with RCC | 1 | 1 | 1.1.2.3 | 0 | FS | 29 | 30 | 29 | 30 | 0 | Yes | 5000 | 0
1.1.2.5 | Ground Soling, Compaction & Flooring | 4 | 1 | 1.1.3.5 | 0 | FS | 30 | 34 | 26 | 30 | 4 | - | 2000 | 3
1.1.3 | First Slab
1.1.3.1 | Columns up to First Slab | 14 | 13 | 1.1.2.4 | 0 | FS | 30 | 44 | 30 | 44 | 0 | Yes | 2000 | 1
1.1.3.2 | Shuttering & Reinforcement of Beams & Slab | 14 | 13 | 1.1.3.1 | 2 | SS | 32 | 46 | 32 | 46 | 0 | Yes | 1000 | 1
1.1.3.3 | Casting of First Floor Beams & Slab | 2 | 1 | 1.1.3.2 | 0 | FS | 46 | 48 | 46 | 48 | 0 | Yes | 1000 | 1
1.1.3.4 | Curing Period | 21 | 21 | 1.1.3.3 | 0 | FS | 48 | 69 | 48 | 69 | 0 | Yes | 1000 | 0
1.1.3.5 | Deshuttering | 7 | 5 | 1.1.3.3 | 0 | FS | 69 | 76 | 69 | 76 | 0 | Yes | 2000 | 2
1.1.4 | Second Floor Tie Beams
1.1.4.1 | Columns up to Tie Beam Bottom | 14 | 12 | 1.1.3.3 | 0 | FS | 76 | 90 | 19 | 33 | 57 | - | 2000 | 2
1.1.4.2 | Shuttering & Reinforcement of Tie Beams | 10 | 9 | 1.1.4.1 | 2 | SS | 78 | 88 | 33 | 35 | 53 | - | 4000 | 1
1.1.4.3 | Casting of Tie Beams with RCC | 1 | 1 | 1.1.4.2 | 0 | FS | 88 | 89 | 36 | 37 | 52 | - | 6000 | 0
1.1.4.4 | Curing Period for Deshuttering | 21 | 18 | 1.1.4.3 | 0 | FS | 89 | 110 | 37 | 58 | 52 | - | 2000 | 3
1.1.4.5 | Deshuttering | 3 | 0 | 1.1.4.4 | 0 | FS | 110 | 113 | 58 | 61 | 52 | - | 4000 | 3
1.1.5 | Truss & Sheeting
1.1.5.1 | Strengthening Period for Tie Beams to Gain Strength | 7 | 7 | 1.1.4.4 | 0 | FS | 110 | 117 | 61 | 68 | 49 | - | 1000 | 0
1.1.5.2 | Truss Erection above Tie Beams | 3 | 2 | 1.1.5.1 | 0 | FS | 117 | 120 | 68 | 71 | 49 | - | 3000 | 1
1.1.5.3 | Sheeting Work | 5 | 3 | 1.1.5.2 | 0 | FS | 120 | 125 | 71 | 76 | 49 | - | 6000 | 2
1.2 | Finishing Work
1.2.1 | Blockwork, Plastering, False Ceiling Work & Tiling
1.2.1.1 | Blockwork and Plaster for Ground Floor | 14 | 14 | 1.1.3.5 | 0 | FS | 76 | 90 | 76 | 90 | 0 | Yes | 1000 | 0
1.2.1.2 | Blockwork and Plaster for First Floor | 18 | 16 | 1.1.4.5 | 0 | FS | 113 | 131 | 20 | 38 | 93 | - | 6000 | 2
1.2.1.3 | False Ceiling Work for First Floor | 8 | 5 | 1.2.1.2 | 0 | FS | 131 | 139 | 38 | 46 | 93 | - | 4000 | 3
1.2.1.4 | Tiles, Skirting & Granite Work for Ground Floor | 12 | 8 | 1.2.1.1 | 0 | FS | 90 | 102 | 46 | 58 | 44 | - | 4000 | 4
1.2.1.5 | Tiles, Skirting & Granite Work for Ground Floor | 12 | 9 | 1.2.1.2 | 0 | FS | 131 | 143 | 58 | 70 | 73 | - | 6000 | 3
1.2.2 | Plumbing & Sanitary Works
1.2.2.1 | Plumbing & Sanitary for Ground Floor | 10 | 9 | 1.2.1.1 | 0 | FS | 90 | 100 | 70 | 80 | 20 | - | 5000 | 1
1.2.2.2 | Plumbing & Sanitary for First Floor | 10 | 9 | 1.2.2.1 | 0 | FS | 100 | 110 | 80 | 90 | 20 | - | 5000 | 1
1.2.3 | Electrification Works
1.2.3.1 | Electrification for Ground Floor | 10 | 8 | 1.2.1.1 | 0 | FS | 90 | 100 | 90 | 100 | 0 | Yes | 3000 | 2
1.2.3.2 | Electrification for First Floor | 10 | 8 | 1.2.3.1 | 0 | FS | 100 | 110 | 70 | 80 | 30 | - | 2000 | 2
1.2.4 | Doors & Windows Fixing
1.2.4.1 | Doors & Windows Fixing for Ground Floor | 10 | 8 | 1.2.1.1 | 0 | FS | 90 | 100 | 80 | 90 | 10 | - | 6000 | 2
1.2.4.2 | Doors & Windows Fixing for First Floor | 10 | 8 | 1.2.2.1 | 0 | FS | 100 | 110 | 90 | 100 | 10 | - | 1000 | 2
1.2.5 | Painting and Finishing
1.2.5.1 | Painting & Finishing for Ground Floor | 15 | 13 | 1.2.3.1 | 0 | FS | 100 | 115 | 100 | 115 | 0 | Yes | 6000 | 2
1.2.5.2 | Painting & Finishing for First Floor | 15 | 13 | 1.2.5.1 | 0 | FS | 115 | 130 | 115 | 130 | 0 | Yes | 4000 | 2
1.2.5.3 | Cleaning of Entire Structure | 5 | 4 | 1.2.5.2 | 0 | FS | 130 | 135 | 130 | 135 | 0 | Yes | 3000 | 1
B | Handover to Client (Finish Milestone) | 0 | 0 | 1.2.5.2 | 0 | FS | 135 | 135 | 135 | 135 | 0 | Yes | 2000 | 0

## Sheet2
Itteration | Activity | Old Duration | New Dration | New Critical Days
D1 | 1.2.1.1 | 18 | 14 | 135
D2 | 1.1.3.5 | 7 | 7
D3 |  | #N/A | #N/A
D4 |  | #N/A | #N/A
|  | #N/A | #N/A
|  | #N/A | #N/A
|  | #N/A | #N/A
|  | #N/A | #N/A
|  | #N/A | #N/A

## Sheet3
Sr No | Steps
1 | Copy a sheet to compare the old and new path
2 | Develop the path
3 | Find out the critical activities (LST-EST)
4 | Filter the critical Activities
5 | Filter the multiple path by Conditional formationg
6 | Use IFERROR(Accrating Cost/Duration difference bw OD and CD,0)
7 | Develop a log to track the changes in schedule
8 | Crash the activities and note in log or table

## Schedule
WBS ID | Activity | Original Duration | Crash duration | Predecessor ID | Lead/(Lag) | Link with Predecessor | Early Start | Early Finish | Late Start | Late Finish | Total Float | Critical Activity | Crash cost per day | Accelarating days
1 | Building Project
A | Site Handover to Contractor (Start Milestone) | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | Yes | 4000 | 0 | 0
1.1 | Structure Work | [13 empty] | 0
1.1.1 | Foundation | [13 empty] | 0
1.1.1.1 | Excavation | 3 | 1 | A | 0 | FS | 0 | 3 | 0 | 3 | 0 | Yes | 3000 | 2 | 6000
1.1.1.2 | PCC | 4 | 3 | 1.1.1.1 | 0 | FS | 3 | 7 | 3 | 7 | 0 | Yes | 1000 | 1 | 1000
1.1.1.3 | Reinforcement & Shuttering | 8 | 7 | 1.1.1.2 | 1 | SS | 4 | 12 | 4 | 12 | 0 | Yes | 3000 | 1 | 3000
1.1.1.4 | Casting with RCC | 8 | 5 | 1.1.1.3 | 1 | SS | 5 | 13 | 5 | 13 | 0 | Yes | 4000 | 3 | 12000
1.1.2 | Plinth Level | [13 empty] | 0
1.1.2.1 | Columns up to Plinth Beam Bottom | 7 | 4 | 1.1.1.4 | 0 | FS | 13 | 20 | 13 | 20 | 0 | Yes | 4000 | 3 | 12000
1.1.2.2 | Backfilling & Compaction | 3 | 2 | 1.1.2.1 | 0 | FS | 20 | 23 | 20 | 23 | 0 | Yes | 2000 | 1 | 2000
1.1.2.3 | Plinth Beam Reinf. & Shuttering | 6 | 5 | 1.1.2.2 | 0 | FS | 23 | 29 | 23 | 29 | 0 | Yes | 1000 | 1 | 1000
1.1.2.4 | Casting of Plinth Beam with RCC | 1 | 1 | 1.1.2.3 | 0 | FS | 29 | 30 | 29 | 30 | 0 | Yes | 5000 | 0 | 0
1.1.2.5 | Ground Soling, Compaction & Flooring | 4 | 1 | 1.1.3.5 | 0 | FS | 30 | 34 | 26 | 30 | 4 | - | 2000 | 3 | 0
1.1.3 | First Slab | [13 empty] | 0
1.1.3.1 | Columns up to First Slab | 14 | 13 | 1.1.2.4 | 0 | FS | 30 | 44 | 30 | 44 | 0 | Yes | 2000 | 1 | 2000
1.1.3.2 | Shuttering & Reinforcement of Beams & Slab | 14 | 13 | 1.1.3.1 | 2 | SS | 32 | 46 | 32 | 46 | 0 | Yes | 1000 | 1 | 1000
1.1.3.3 | Casting of First Floor Beams & Slab | 2 | 1 | 1.1.3.2 | 0 | FS | 46 | 48 | 46 | 48 | 0 | Yes | 1000 | 1 | 1000
1.1.3.4 | Curing Period | 21 | 21 | 1.1.3.3 | 0 | FS | 48 | 69 | 48 | 69 | 0 | Yes | 1000 | 0 | 0
1.1.3.5 | Deshuttering | 7 | 5 | 1.1.3.3 | 0 | FS | 69 | 76 | 69 | 76 | 0 | Yes | 2000 | 2 | 4000
1.1.4 | Second Floor Tie Beams | [13 empty] | 0
1.1.4.1 | Columns up to Tie Beam Bottom | 14 | 12 | 1.1.3.3 | 0 | FS | 76 | 90 | 19 | 33 | 57 | - | 2000 | 2 | 0
1.1.4.2 | Shuttering & Reinforcement of Tie Beams | 10 | 9 | 1.1.4.1 | 2 | SS | 78 | 88 | 33 | 35 | 53 | - | 4000 | 1 | 0
1.1.4.3 | Casting of Tie Beams with RCC | 1 | 1 | 1.1.4.2 | 0 | FS | 88 | 89 | 36 | 37 | 52 | - | 6000 | 0 | 0
1.1.4.4 | Curing Period for Deshuttering | 21 | 18 | 1.1.4.3 | 0 | FS | 89 | 110 | 37 | 58 | 52 | - | 2000 | 3 | 0
1.1.4.5 | Deshuttering | 3 | 0 | 1.1.4.4 | 0 | FS | 110 | 113 | 58 | 61 | 52 | - | 4000 | 3 | 0
1.1.5 | Truss & Sheeting | [13 empty] | 0
1.1.5.1 | Strengthening Period for Tie Beams to Gain Strength | 7 | 7 | 1.1.4.4 | 0 | FS | 110 | 117 | 61 | 68 | 49 | - | 1000 | 0 | 0
1.1.5.2 | Truss Erection above Tie Beams | 3 | 2 | 1.1.5.1 | 0 | FS | 117 | 120 | 68 | 71 | 49 | - | 3000 | 1 | 0
1.1.5.3 | Sheeting Work | 5 | 3 | 1.1.5.2 | 0 | FS | 120 | 125 | 71 | 76 | 49 | - | 6000 | 2 | 0
1.2 | Finishing Work | [13 empty] | 0
1.2.1 | Blockwork, Plastering, False Ceiling Work & Tiling | [13 empty] | 0
1.2.1.1 | Blockwork and Plaster for Ground Floor | 18 | 14 | 1.1.3.5 | 0 | FS | 76 | 94 | 76 | 94 | 0 | Yes | 1000 | 4 | 4000
1.2.1.2 | Blockwork and Plaster for First Floor | 18 | 16 | 1.1.4.5 | 0 | FS | 113 | 131 | 24 | 42 | 89 | - | 6000 | 2 | 0
1.2.1.3 | False Ceiling Work for First Floor | 8 | 5 | 1.2.1.2 | 0 | FS | 131 | 139 | 42 | 50 | 89 | - | 4000 | 3 | 0
1.2.1.4 | Tiles, Skirting & Granite Work for Ground Floor | 12 | 8 | 1.2.1.1 | 0 | FS | 94 | 106 | 50 | 62 | 44 | - | 4000 | 4 | 0
1.2.1.5 | Tiles, Skirting & Granite Work for Ground Floor | 12 | 9 | 1.2.1.2 | 0 | FS | 131 | 143 | 62 | 74 | 69 | - | 6000 | 3 | 0
1.2.2 | Plumbing & Sanitary Works | [13 empty] | 0
1.2.2.1 | Plumbing & Sanitary for Ground Floor | 10 | 9 | 1.2.1.1 | 0 | FS | 94 | 104 | 74 | 84 | 20 | - | 5000 | 1 | 0
1.2.2.2 | Plumbing & Sanitary for First Floor | 10 | 9 | 1.2.2.1 | 0 | FS | 104 | 114 | 84 | 94 | 20 | - | 5000 | 1 | 0
1.2.3 | Electrification Works | [13 empty] | 0
1.2.3.1 | Electrification for Ground Floor | 10 | 8 | 1.2.1.1 | 0 | FS | 94 | 104 | 94 | 104 | 0 | Yes | 3000 | 2 | 6000
1.2.3.2 | Electrification for First Floor | 10 | 8 | 1.2.3.1 | 0 | FS | 104 | 114 | 74 | 84 | 30 | - | 2000 | 2 | 0
1.2.4 | Doors & Windows Fixing | [13 empty] | 0
1.2.4.1 | Doors & Windows Fixing for Ground Floor | 10 | 8 | 1.2.1.1 | 0 | FS | 94 | 104 | 84 | 94 | 10 | - | 6000 | 2 | 0
1.2.4.2 | Doors & Windows Fixing for First Floor | 10 | 8 | 1.2.2.1 | 0 | FS | 104 | 114 | 94 | 104 | 10 | - | 1000 | 2 | 0
1.2.5 | Painting and Finishing | [13 empty] | 0
1.2.5.1 | Painting & Finishing for Ground Floor | 15 | 13 | 1.2.3.1 | 0 | FS | 104 | 119 | 104 | 119 | 0 | Yes | 6000 | 2 | 12000
1.2.5.2 | Painting & Finishing for First Floor | 15 | 13 | 1.2.5.1 | 0 | FS | 119 | 134 | 119 | 134 | 0 | Yes | 4000 | 2 | 8000
1.2.5.3 | Cleaning of Entire Structure | 5 | 4 | 1.2.5.2 | 0 | FS | 134 | 139 | 134 | 139 | 0 | Yes | 3000 | 1 | 3000
B | Handover to Client (Finish Milestone) | 0 | 0 | 1.2.5.2 | 0 | FS | 139 | 139 | 139 | 139 | 0 | Yes | 2000 | 0 | 0
78000

## By Solver
130 | 131 | [12 empty] | 1000
WBS ID | Activity | OriginHal Duration | Original Duration | Crash duration | Predecessor ID | Lead/(Lag) | Link with Predecessor | Early Start | Early Finish | Late Start | Late Finish | Total Float | Critical Activity | Crash cost per day | Accelarating days
1 | Building Project | [12 empty] | 0
A | Site Handover to Contractor (Start Milestone) | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | Yes | 4000 | 0 | 0
1.1 | Structure Work | [12 empty] | 0 | - | 0
1.1.1 | Foundation | [12 empty] | 0 | - | 0
1.1.1.1 | Excavation | 3 | 3 | 1 | A | 0 | FS | 0 | 3 | 0 | 3 | 0 | Yes | 3000 | 2 | 6000 | 14000
1.1.1.2 | PCC | 4 | 4 | 3 | 1.1.1.1 | 0 | FS | 3 | 7 | 3 | 7 | 0 | Yes | 1000 | 1 | 1000 | 19000
1.1.1.3 | Reinforcement & Shuttering | 8 | 8 | 7 | 1.1.1.2 | 1 | SS | 4 | 12 | 4 | 12 | 0 | Yes | 3000 | 1 | 3000 | 17000
1.1.1.4 | Casting with RCC | 8 | 8 | 5 | 1.1.1.3 | 1 | SS | 5 | 13 | 5 | 13 | 0 | Yes | 4000 | 3 | 12000 | 8000
1.1.2 | Plinth Level | 0 | 0 | 0 | [9 empty] | 0 | - | 0
1.1.2.1 | Columns up to Plinth Beam Bottom | 7 | 7 | 4 | 1.1.1.4 | 0 | FS | 13 | 20 | 13 | 20 | 0 | Yes | 4000 | 3 | 12000 | 8000
1.1.2.2 | Backfilling & Compaction | 3 | 3 | 2 | 1.1.2.1 | 0 | FS | 20 | 23 | 20 | 23 | 0 | Yes | 2000 | 1 | 2000 | 18000
1.1.2.3 | Plinth Beam Reinf. & Shuttering | 6 | 5 | 5 | 1.1.2.2 | 0 | FS | 23 | 28 | 23 | 28 | 0 | Yes | 1000 | 0 | 0 | 20000
1.1.2.4 | Casting of Plinth Beam with RCC | 1 | 1 | 1 | 1.1.2.3 | 0 | FS | 28 | 29 | 28 | 29 | 0 | Yes | 5000 | 0 | 0 | 20000
1.1.2.5 | Ground Soling, Compaction & Flooring | 4 | 1 | 1 | 1.1.3.5 | 0 | FS | 29 | 30 | 28 | 29 | 1 | - | 2000 | - | 0 | 20000
1.1.3 | First Slab | 0 | 0 | 0 | [9 empty] | 0 | - | 0
1.1.3.1 | Columns up to First Slab | 14 | 13 | 13 | 1.1.2.4 | 0 | FS | 29 | 42 | 29 | 42 | 0 | Yes | 2000 | 0 | 0 | 20000
1.1.3.2 | Shuttering & Reinforcement of Beams & Slab | 14 | 13 | 13 | 1.1.3.1 | 2 | SS | 31 | 44 | 31 | 44 | 0 | Yes | 1000 | 0 | 0 | 20000
1.1.3.3 | Casting of First Floor Beams & Slab | 2 | 1 | 1 | 1.1.3.2 | 0 | FS | 44 | 45 | 44 | 45 | 0 | Yes | 1000 | 0 | 0 | 20000
1.1.3.4 | Curing Period | 21 | 21 | 21 | 1.1.3.3 | 0 | FS | 45 | 66 | 45 | 66 | 0 | Yes | 1000 | 0 | 0 | 20000
1.1.3.5 | Deshuttering | 7 | 6 | 5 | 1.1.3.3 | 0 | FS | 66 | 72 | 66 | 72 | 0 | Yes | 2000 | 1 | 2000 | 18000
1.1.4 | Second Floor Tie Beams | 0 | 0 | 0 | [9 empty] | 0 | - | 0
1.1.4.1 | Columns up to Tie Beam Bottom | 14 | 13 | 12 | 1.1.3.3 | 0 | FS | 72 | 85 | 25 | 38 | 47 | - | 2000 | - | 0 | 20000
1.1.4.2 | Shuttering & Reinforcement of Tie Beams | 10 | 9 | 9 | 1.1.4.1 | 2 | SS | 74 | 83 | 38 | 40 | 43 | - | 4000 | - | 0 | 20000
1.1.4.3 | Casting of Tie Beams with RCC | 1 | 1 | 1 | 1.1.4.2 | 0 | FS | 83 | 84 | 41 | 42 | 42 | - | 6000 | - | 0 | 20000
1.1.4.4 | Curing Period for Deshuttering | 21 | 18 | 18 | 1.1.4.3 | 0 | FS | 84 | 102 | 42 | 60 | 42 | - | 2000 | - | 0 | 20000
1.1.4.5 | Deshuttering | 3 | 0 | 0 | 1.1.4.4 | 0 | FS | 102 | 102 | 60 | 60 | 42 | - | 4000 | - | 0 | 20000
1.1.5 | Truss & Sheeting | 0 | 0 | 0 | [9 empty] | 0 | - | 0
1.1.5.1 | Strengthening Period for Tie Beams to Gain Strength | 7 | 7 | 7 | 1.1.4.4 | 0 | FS | 102 | 109 | 60 | 67 | 42 | - | 1000 | - | 0 | 20000
1.1.5.2 | Truss Erection above Tie Beams | 3 | 2 | 2 | 1.1.5.1 | 0 | FS | 109 | 111 | 67 | 69 | 42 | - | 3000 | - | 0 | 20000
1.1.5.3 | Sheeting Work | 5 | 3 | 3 | 1.1.5.2 | 0 | FS | 111 | 114 | 69 | 72 | 42 | - | 6000 | - | 0 | 20000
1.2 | Finishing Work | 0 | 0 | 0 | [9 empty] | 0 | - | 0
1.2.1 | Blockwork, Plastering, False Ceiling Work & Tiling | 0 | 0 | 0 | [9 empty] | 0 | - | 0
1.2.1.1 | Blockwork and Plaster for Ground Floor | 18 | 14 | 14 | 1.1.3.5 | 0 | FS | 72 | 86 | 72 | 86 | 0 | Yes | 1000 | 0 | 0 | 20000
1.2.1.2 | Blockwork and Plaster for First Floor | 18 | 16 | 16 | 1.1.4.5 | 0 | FS | 102 | 118 | 24 | 40 | 78 | - | 6000 | - | 0 | 20000
1.2.1.3 | False Ceiling Work for First Floor | 8 | 7 | 5 | 1.2.1.2 | 0 | FS | 118 | 125 | 40 | 47 | 78 | - | 4000 | - | 0 | 20000
1.2.1.4 | Tiles, Skirting & Granite Work for Ground Floor | 12 | 8 | 8 | 1.2.1.1 | 0 | FS | 86 | 94 | 47 | 55 | 39 | - | 4000 | - | 0 | 20000
1.2.1.5 | Tiles, Skirting & Granite Work for Ground Floor | 12 | 11 | 9 | 1.2.1.2 | 0 | FS | 118 | 129 | 55 | 66 | 63 | - | 6000 | - | 0 | 20000
1.2.2 | Plumbing & Sanitary Works | 0 | 0 | 0 | [9 empty] | 0 | - | 0
1.2.2.1 | Plumbing & Sanitary for Ground Floor | 10 | 10 | 9 | 1.2.1.1 | 0 | FS | 86 | 96 | 66 | 76 | 20 | - | 5000 | - | 0 | 20000
1.2.2.2 | Plumbing & Sanitary for First Floor | 10 | 10 | 9 | 1.2.2.1 | 0 | FS | 96 | 106 | 76 | 86 | 20 | - | 5000 | - | 0 | 20000
1.2.3 | Electrification Works | 0 | 0 | 0 | [9 empty] | 0 | - | 0
1.2.3.1 | Electrification for Ground Floor | 10 | 10 | 8 | 1.2.1.1 | 0 | FS | 86 | 96 | 86 | 96 | 0 | Yes | 3000 | 2 | 6000 | 14000
1.2.3.2 | Electrification for First Floor | 10 | 9 | 8 | 1.2.3.1 | 0 | FS | 96 | 105 | 70 | 79 | 26 | - | 2000 | - | 0 | 20000
1.2.4 | Doors & Windows Fixing | 0 | 0 | 0 | [9 empty] | 0 | - | 0
1.2.4.1 | Doors & Windows Fixing for Ground Floor | 10 | 8 | 8 | 1.2.1.1 | 0 | FS | 86 | 94 | 79 | 87 | 7 | - | 6000 | - | 0 | 20000
1.2.4.2 | Doors & Windows Fixing for First Floor | 10 | 9 | 8 | 1.2.2.1 | 0 | FS | 96 | 105 | 87 | 96 | 9 | - | 1000 | - | 0 | 20000
1.2.5 | Painting and Finishing | 0 | 0 | 0 | [9 empty] | 0 | - | 0
1.2.5.1 | Painting & Finishing for Ground Floor | 15 | 15 | 13 | 1.2.3.1 | 0 | FS | 96 | 111 | 96 | 111 | 0 | Yes | 6000 | 2 | 12000 | 8000
1.2.5.2 | Painting & Finishing for First Floor | 15 | 15 | 13 | 1.2.5.1 | 0 | FS | 111 | 126 | 111 | 126 | 0 | Yes | 4000 | 2 | 8000 | 12000
1.2.5.3 | Cleaning of Entire Structure | 5 | 5 | 4 | 1.2.5.2 | 0 | FS | 126 | 131 | 126 | 131 | 0 | Yes | 3000 | 1 | 3000 | 17000
B | Handover to Client (Finish Milestone) | 0 | 0 | 0 | 1.2.5.2 | 0 | FS | 131 | 131 | 131 | 131 | 0 | Yes | 2000 | 0 | 0
[10 empty] | 130 | 131 |  |  |  | - | 67000 | 653000

## By Solver (2)
129 | 129 | [12 empty] | 1000
WBS ID | Activity | OriginHal Duration | Original Duration | Crash duration | Predecessor ID | Lead/(Lag) | Link with Predecessor | Early Start | Early Finish | Late Start | Late Finish | Total Float | Critical Activity | Crash cost per day | Accelarating days
1 | Building Project | [12 empty] | 0
A | Site Handover to Contractor (Start Milestone) | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | Yes | 4000 | 0 | 0
1.1 | Structure Work | [12 empty] | 0 | - | 0
1.1.1 | Foundation | [12 empty] | 0 | - | 0
1.1.1.1 | Excavation | 3 | 3 | 1 | A | 0 | FS | 0 | 3 | 0 | 3 | 0 | Yes | 3000 | 2 | 6000 | 14000
1.1.1.2 | PCC | 4 | 4 | 3 | 1.1.1.1 | 0 | FS | 3 | 7 | 3 | 7 | 0 | Yes | 1000 | 1 | 1000 | 19000
1.1.1.3 | Reinforcement & Shuttering | 8 | 8 | 7 | 1.1.1.2 | 1 | SS | 4 | 12 | 4 | 12 | 0 | Yes | 3000 | 1 | 3000 | 17000
1.1.1.4 | Casting with RCC | 8 | 8 | 5 | 1.1.1.3 | 1 | SS | 5 | 13 | 5 | 13 | 0 | Yes | 4000 | 3 | 12000 | 8000
1.1.2 | Plinth Level | 0 | 0 | 0 | [9 empty] | 0 | - | 0
1.1.2.1 | Columns up to Plinth Beam Bottom | 7 | 7 | 4 | 1.1.1.4 | 0 | FS | 13 | 20 | 13 | 20 | 0 | Yes | 4000 | 3 | 12000 | 8000
1.1.2.2 | Backfilling & Compaction | 3 | 2 | 2 | 1.1.2.1 | 0 | FS | 20 | 22 | 20 | 22 | 0 | Yes | 2000 | 0 | 0 | 20000
1.1.2.3 | Plinth Beam Reinf. & Shuttering | 6 | 5 | 5 | 1.1.2.2 | 0 | FS | 22 | 27 | 22 | 27 | 0 | Yes | 1000 | 0 | 0 | 20000
1.1.2.4 | Casting of Plinth Beam with RCC | 1 | 1 | 1 | 1.1.2.3 | 0 | FS | 27 | 28 | 27 | 28 | 0 | Yes | 5000 | 0 | 0 | 20000
1.1.2.5 | Ground Soling, Compaction & Flooring | 4 | 1 | 1 | 1.1.3.5 | 0 | FS | 28 | 29 | 27 | 28 | 1 | - | 2000 | - | 0 | 20000
1.1.3 | First Slab | 0 | 0 | 0 | [9 empty] | 0 | - | 0
1.1.3.1 | Columns up to First Slab | 14 | 13 | 13 | 1.1.2.4 | 0 | FS | 28 | 41 | 28 | 41 | 0 | Yes | 2000 | 0 | 0 | 20000
1.1.3.2 | Shuttering & Reinforcement of Beams & Slab | 14 | 13 | 13 | 1.1.3.1 | 2 | SS | 30 | 43 | 30 | 43 | 0 | Yes | 1000 | 0 | 0 | 20000
1.1.3.3 | Casting of First Floor Beams & Slab | 2 | 1 | 1 | 1.1.3.2 | 0 | FS | 43 | 44 | 43 | 44 | 0 | Yes | 1000 | 0 | 0 | 20000
1.1.3.4 | Curing Period | 21 | 21 | 21 | 1.1.3.3 | 0 | FS | 44 | 65 | 44 | 65 | 0 | Yes | 1000 | 0 | 0 | 20000
1.1.3.5 | Deshuttering | 7 | 5 | 5 | 1.1.3.3 | 0 | FS | 65 | 70 | 65 | 70 | 0 | Yes | 2000 | 0 | 0 | 20000
1.1.4 | Second Floor Tie Beams | 0 | 0 | 0 | [9 empty] | 0 | - | 0
1.1.4.1 | Columns up to Tie Beam Bottom | 14 | 12 | 12 | 1.1.3.3 | 0 | FS | 70 | 82 | 24 | 36 | 46 | - | 2000 | - | 0 | 20000
1.1.4.2 | Shuttering & Reinforcement of Tie Beams | 10 | 9 | 9 | 1.1.4.1 | 2 | SS | 72 | 81 | 36 | 38 | 43 | - | 4000 | - | 0 | 20000
1.1.4.3 | Casting of Tie Beams with RCC | 1 | 1 | 1 | 1.1.4.2 | 0 | FS | 81 | 82 | 39 | 40 | 42 | - | 6000 | - | 0 | 20000
1.1.4.4 | Curing Period for Deshuttering | 21 | 18 | 18 | 1.1.4.3 | 0 | FS | 82 | 100 | 40 | 58 | 42 | - | 2000 | - | 0 | 20000
1.1.4.5 | Deshuttering | 3 | 0 | 0 | 1.1.4.4 | 0 | FS | 100 | 100 | 58 | 58 | 42 | - | 4000 | - | 0 | 20000
1.1.5 | Truss & Sheeting | 0 | 0 | 0 | [9 empty] | 0 | - | 0
1.1.5.1 | Strengthening Period for Tie Beams to Gain Strength | 7 | 7 | 7 | 1.1.4.4 | 0 | FS | 100 | 107 | 58 | 65 | 42 | - | 1000 | - | 0 | 20000
1.1.5.2 | Truss Erection above Tie Beams | 3 | 2 | 2 | 1.1.5.1 | 0 | FS | 107 | 109 | 65 | 67 | 42 | - | 3000 | - | 0 | 20000
1.1.5.3 | Sheeting Work | 5 | 3 | 3 | 1.1.5.2 | 0 | FS | 109 | 112 | 67 | 70 | 42 | - | 6000 | - | 0 | 20000
1.2 | Finishing Work | 0 | 0 | 0 | [9 empty] | 0 | - | 0
1.2.1 | Blockwork, Plastering, False Ceiling Work & Tiling | 0 | 0 | 0 | [9 empty] | 0 | - | 0
1.2.1.1 | Blockwork and Plaster for Ground Floor | 18 | 14 | 14 | 1.1.3.5 | 0 | FS | 70 | 84 | 70 | 84 | 0 | Yes | 1000 | 0 | 0 | 20000
1.2.1.2 | Blockwork and Plaster for First Floor | 18 | 16 | 16 | 1.1.4.5 | 0 | FS | 100 | 116 | 28 | 44 | 72 | - | 6000 | - | 0 | 20000
1.2.1.3 | False Ceiling Work for First Floor | 8 | 5 | 5 | 1.2.1.2 | 0 | FS | 116 | 121 | 44 | 49 | 72 | - | 4000 | - | 0 | 20000
1.2.1.4 | Tiles, Skirting & Granite Work for Ground Floor | 12 | 8 | 8 | 1.2.1.1 | 0 | FS | 84 | 92 | 49 | 57 | 35 | - | 4000 | - | 0 | 20000
1.2.1.5 | Tiles, Skirting & Granite Work for Ground Floor | 12 | 9 | 9 | 1.2.1.2 | 0 | FS | 116 | 125 | 57 | 66 | 59 | - | 6000 | - | 0 | 20000
1.2.2 | Plumbing & Sanitary Works | 0 | 0 | 0 | [9 empty] | 0 | - | 0
1.2.2.1 | Plumbing & Sanitary for Ground Floor | 10 | 9 | 9 | 1.2.1.1 | 0 | FS | 84 | 93 | 66 | 75 | 18 | - | 5000 | - | 0 | 20000
1.2.2.2 | Plumbing & Sanitary for First Floor | 10 | 9 | 9 | 1.2.2.1 | 0 | FS | 93 | 102 | 75 | 84 | 18 | - | 5000 | - | 0 | 20000
1.2.3 | Electrification Works | 0 | 0 | 0 | [9 empty] | 0 | - | 0
1.2.3.1 | Electrification for Ground Floor | 10 | 10 | 8 | 1.2.1.1 | 0 | FS | 84 | 94 | 84 | 94 | 0 | Yes | 3000 | 2 | 6000 | 14000
1.2.3.2 | Electrification for First Floor | 10 | 8 | 8 | 1.2.3.1 | 0 | FS | 94 | 102 | 69 | 77 | 25 | - | 2000 | - | 0 | 20000
1.2.4 | Doors & Windows Fixing | 0 | 0 | 0 | [9 empty] | 0 | - | 0
1.2.4.1 | Doors & Windows Fixing for Ground Floor | 10 | 9 | 8 | 1.2.1.1 | 0 | FS | 84 | 93 | 77 | 86 | 7 | - | 6000 | - | 0 | 20000
1.2.4.2 | Doors & Windows Fixing for First Floor | 10 | 8 | 8 | 1.2.2.1 | 0 | FS | 93 | 101 | 86 | 94 | 7 | - | 1000 | - | 0 | 20000
1.2.5 | Painting and Finishing | 0 | 0 | 0 | [9 empty] | 0 | - | 0
1.2.5.1 | Painting & Finishing for Ground Floor | 15 | 15 | 13 | 1.2.3.1 | 0 | FS | 94 | 109 | 94 | 109 | 0 | Yes | 6000 | 2 | 12000 | 8000
1.2.5.2 | Painting & Finishing for First Floor | 15 | 15 | 13 | 1.2.5.1 | 0 | FS | 109 | 124 | 109 | 124 | 0 | Yes | 4000 | 2 | 8000 | 12000
1.2.5.3 | Cleaning of Entire Structure | 5 | 5 | 4 | 1.2.5.2 | 0 | FS | 124 | 129 | 124 | 129 | 0 | Yes | 3000 | 1 | 3000 | 17000
B | Handover to Client (Finish Milestone) | 0 | 0 | 0 | 1.2.5.2 | 0 | FS | 129 | 129 | 129 | 129 | 0 | Yes | 2000 | 0 | 0
[10 empty] | 129 | 129 |  |  |  | - | 63000 | 657000