## Question
Conduct Resource Allocation and Levelling for the following network. Can the work be performed with maximum 6 labourers without delaying the project? Has the critical path (or critical activities) changed after resource levelling excerise? What would you do if the maximum possible labour is 5 each day?
Activity | Preceeding activity (FS) | Duration | Laborers | EST | EFT | LST | LFT | Critical Activity (Yes/No) | Float
A | - | 5 | 2 | 0 | 5 | 2 | 7 | No | 2
B | - | 7 | 4 | 0 | 7 | 0 | 7 | Yes | 0
C | A | 3 | 3 | 5 | 8 | 9 | 12 | No | 4
D | A,B | 5 | 3 | 7 | 12 | 7 | 12 | Yes | 0
E | C,D | 2 | 2 | 12 | 14 | 12 | 14 | Yes | 0

## Solution
Ans 1 | [7 empty] | Ans 2 | Yes
Days | A | B | C | D | E | Total Laboures |  | Days | A | B | C | D | E | Total Laboures
1 | 2 | 4 |  |  |  | 6 |  | 1 | 2 | 4 |  |  |  | 6
2 | 2 | 4 |  |  |  | 6 |  | 2 | 2 | 4 |  |  |  | 6
3 | 2 | 4 |  |  |  | 6 |  | 3 | 2 | 4 |  |  |  | 6
4 | 2 | 4 |  |  |  | 6 |  | 4 | 2 | 4 |  |  |  | 6
5 | 2 | 4 |  |  |  | 6 |  | 5 | 2 | 4 |  |  |  | 6
6 |  | 4 | 3 |  |  | 7 |  | 6 |  | 4 | 2 |  |  | 6
7 |  | 4 | 3 |  |  | 7 |  | 7 |  | 4 | 2 |  |  | 6
8 |  |  | 3 | 3 |  | 6 |  | 8 |  |  | 3 | 3 |  | 6
9 |  |  |  | 3 |  | 3 |  | 9 |  |  | 2 | 3 |  | 5
10 |  |  |  | 3 |  | 3 |  | 10 |  |  |  | 3 |  | 3
11 |  |  |  | 3 |  | 3 |  | 11 |  |  |  | 3 |  | 3
12 |  |  |  | 3 |  | 3 |  | 12 |  |  |  | 3 |  | 3
13 |  |  |  |  | 2 | 2 |  | 13 |  |  |  |  | 2 | 2
14 |  |  |  |  | 2 | 2 |  | 14 |  |  |  |  | 2 | 2
Ans 4
Ans 3 | Initial CA: B, D, E | [9 empty] | Days | A | B | C | D | E | Total Laboures
| After Resource Allocation:B, D,E | [9 empty] | 1 | 1 | 4 |  |  |  | 5
| Therefore No change in CA | [9 empty] | 2 | 1 | 4 |  |  |  | 5
Activity | Preceeding activity (FS) | Duration | Laborers | EST | EFT | LST | LFT | Critical Activity (Yes/No) | Float |  | 3 | 1 | 4 |  |  |  | 5
A | - | 5 | 2 | 0 | 5 | 2 | 7 | No | 2 |  | 4 | 1 | 4 |  |  |  | 5
B | - | 7 | 4 | 0 | 7 | 0 | 7 | Yes | 0 |  | 5 | 1 | 4 |  |  |  | 5
C | A | 4 | 3 | 5 | 9 | 9 | 13 | No | 4 |  | 6 | 1 | 4 | 0 |  |  | 5
D | A,B | 5 | 3 | 7 | 12 | 7 | 12 | Yes | 0 |  | 7 | 4 | 4 | 0 |  |  | 8 | From here no more allocation can be done because activity A and activity B has reached there maximum float
E | C,D | 2 | 2 | 12 | 14 | 12 | 14 | Yes | 0 |  | 8 |  |  | 3 | 3 |  | 6
[11 empty] | 9 |  |  | 2 | 3 |  | 5
[11 empty] | 10 |  |  | 2 | 3 |  | 5
[11 empty] | 11 |  |  | 2 | 3 |  | 5
[11 empty] | 12 |  |  |  | 3 |  | 3
[11 empty] | 13 |  |  |  |  | 2 | 2
[11 empty] | 14 |  |  |  |  | 2 | 2